## Status
S.No | Requirements | Requirement Details | Total Test Cases | Descoped | Revised Total test cases | Total Executed | Total |  |  | Today Executed | Today |  |  | Pending to Pass | Execution Completion % | Pass Percentage % | Tester | Dev Status
[7 empty] | Passed | Failed | WIP |  | Passed | Failed | WIP
1 | CASHPAY-4259 | Creating a Group Chat | 12 | 0 | 12 | 5 | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 7 | 41.67% | 41.67% | Ganesh | Dev Completed
2 | CASHPAY-5678 | Adding Images and Emojis and Stickers | 14 | 2 | 12 | 12 | 9 | 1 | 2 | 6 | 0 | 0 | 0 | 0 | 100% | 75% | Prabha | Dev Completed
3 | CASHPAY-6321 | Removing Partipants from Chat | 11 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0% | 0% | Ganesh | Yet to Deploy
4 | CASHPAY-7231 | Adding Videos or Photos in Chat | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0% | 0% | Prabha | Yet to Deploy
5 | CASHPAY-7232 | Message Delivery time creation | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0% | 0% | Ganesh | Yet to Deploy
Total |  |  | 70 | 5 | 65 | 17 | 14 | 1 | 2 | 11 | 5 | 0 | 0 | 51 | 26.15% | 21.54%

## Downtime
S.No | Application | Hours Down Today | Total | Remarks
1 | Credit Card Team | 5 Hrs | 5 hrs | Due to Technical Issue
2 | Catch | 0 | 0
3 | Database | 1 Hr | 1 Hrs | Dataserver Error

## Defect Details
S.No | Defect ID | Defect Summary | User Story | Assignee | Status | Aging
1 | CASHPAY-8001 | Unable to add Emoji in Chat | CASHPAY-5678 | Chandru | Open | 5
2 | CASHPAY-8041 | Unable to use different fonts | CASHPAY-5678 | Chandru | Closed | 0

## RAG Status
IT Planned End Date | RAG STATUS
2021-09-19 | Green

## Sheet1
PB-2345 | TC_UT_01 | TC_IT_01 | TC_SIT_01 | TC_UAT_01
| TC_UT_02 | TC_IT_02 | TC_SIT_02 | TC_UAT_02
|  | TC_IT_03 | TC_SIT_03 | TC_UAT_03
|  | TC_IT_04 | TC_SIT_04 | TC_UAT_04
|  | TC_IT_05 | TC_SIT_05 | TC_UAT_05
|  | TC_IT_06 | TC_SIT_06 | TC_UAT_06
|  | TC_IT_07 | TC_SIT_07 | TC_UAT_07
|  | TC_IT_08 | TC_SIT_08 | TC_UAT_08
|  | TC_IT_09 | TC_SIT_09 | TC_UAT_09
|  | TC_IT_10 |  | TC_UAT_10
|  | TC_IT_11 |  | TC_UAT_11
|  | TC_IT_12 |  | TC_UAT_12
|  | TC_IT_13 |  | TC_UAT_13
|  | TC_IT_14 |  | TC_UAT_14
|  | TC_IT_15 |  | TC_UAT_15
|  | TC_IT_16 |  | TC_UAT_16
|  | TC_IT_17 |  | TC_UAT_17
TC_IT_18
TC_IT_19
TC_IT_20
TC_IT_21